## BackLog
Item | Type | Size/Days | Priority
view menu (Foods & Beverage) | Features | 2 | 1
manage menu item (food & beverage) (name & price) | Features | 4 | 2
view picture of menu | Features | 1 | 3
manage item picture | Features | 2 | 4
view ingredients of menu item | Features | 1 | 5
manage menu ingredients | Features | 2 | 6
view menu item duration | Features | 1 | 7
manage item duration | Features | 2 | 8
order menu | Features | 2 | 9
view customers order by table number | Features | 1 | 10
view bill | Features | 1 | 11
request bill | Features | 1 | 12
view customers bill request | Features | 1 | 13
print bill | Features | 2 | 14
view order status | Features | 1 | 15
view item requests to be cooked | Features | 1 | 16
update item request status | Features | 1 | 17
add review | Features | 2 | 18
view customers' review on item | Features | 1 | 19
view customers' review on restaurant | Features | 1 | 20
view total sales | Features | 2 | 21
view favourites item | Features | 2 | 22
view ingredients stock | Features | 1 | 23
view low stock of ingredients | Features | 1 | 24
view ingredients stock detail with expired date | Features | 2 | 25
view menu item ingredients detail for cooking | Features | 1 | 26
view menu item cooking recipe (step by step) | Features | 1 | 27
manage cooking recipes | Features | 4 | 28

## user stories
Viewing the Order | As a cashier I want to know what the customer ordered on each table
Viewing the bill request | As a cashier I want to know whenever the customer request the bill
Updating status | As a cook I want to be make that I am currently cooking a meal from the request or done cooking
Viewing item recipe | As a cook I want to know each recipe for each item
Viewing stock | As a cook I want to know how many ingredients currently available
Viewing item ingredients | As a cook I want to know how many ingredients needed for each item
Viewing item review | As a cook I want to know the customer review for each food item I cooked
Viewing Item request | As a cook I want to know what food / drink currently requested
Requesting the bill | As a customer I want to be able to request a bill to be delivered
Viewing menu list | As a customer I want to be able to see all items in the restaurant with the prices
Viewing the picture | As a customer I want to be able to see all of the picture of the items in the menu
Viewing the bill | As a customer I want to know how many I need pay
Knowing the duration | As a customer I want to know the duration of each item
Knowing the status | As a customer I want to know the status of the item I ordered whether is in queue, working on process, on delivery, or arrived
Viewing the ingredients | As a customer I want to know what ingredients used on each item
Filtering Ingredients Stock | As an owner I want to be able to view what ingredients that currently low on stock
Viewing customer review | As an owner I want to know customers review for the restaurant and item
Viewing the sales | As an owner I want to know total sales for each day, week and month
Viewing ingredients expired list | As an owner I want to know what ingredients have already expired
Viewing item trends | As an owner I want to know what items is most popular

## Sprint1
Feature: view menu (Foods & Beverage)
Task Name | Duration | PIC | hours
HTML mockup | 6 hours | IK | 6
code the UI | 4 hours | CI, GV | 4
icon & css design | 12 hours | GV | 12
code the service | 6 hours | ER | 6
test scenario for UI | 8 hours | CS | 8
test scenario for service | 6 hours | EC | 6
design the table | 8 hours | RI | 8
code the table migration | 4 hours | CA | 4
54