## 12 Mei (1)
Task | D1 | D2 | D3 | D4 | D5 | D6
Order Menu | 5 | 3 | 3 | 2
View Customer Order by table Number | D2: 4; D3: 4; D4: 2
View Bill |  |  | 4 | 2 | 2 | 2
Request Bill |  |  | 4 | 2 | 2 | 2
View Customer bill request | D4: 6; D5: 4; D6: 2
Total | 5 | 7 | 15 | 14 | 8 | 6
Note on B2: Design
Note on C2: Database
Note on D2: Backend
Note on E2: Tester
Note on C3: Design
Note on D3: Backend
Note on E3: Tester
Note on D4: Design
Note on E4: Database
Note on F4: Backend
Note on G4: Testing
Note on D5: Design
Note on E5: Database
Note on F5: Backend
Note on G5: Testing
Note on E6: Design
Note on F6: Backend
Note on G6: Tester

## 12 Mei (2)
Task |  | PIC | Duration
Order Menu
| -Design | DJ | 5
| -Backend | KV, MM | 3
| -Database | YA | 3
| -Tester | OI | 2
| -Analysis | MM | 1
| -Scrum Master | MA | 1
View Customer Order by table Number
| -Design | DJ | 4
| -Backend | KV | 4
| -Database | YA | 0
| -Tester | OI | 2
| -Analysis | MM | 1
| -Scrum Master | MA | 1
View Bill
| -Design | DJ | 4
| -Backend | MM | 2
| -Database | YA | 2
| -Tester | OI | 2
| -Analysis | MM | 1
| -Scrum Master | MA | 1
Request Bill
| -Design | DJ | 4
| -Backend | MM | 2
| -Database | YA | 2
| -Tester | OI | 2
| -Analysis | MM | 1
| -Scrum Master | MA | 1
View Customer bill request
| -Design | DJ | 6
| -Backend | MM | 4
| -Database | YA | 0
| -Tester | OI | 2
| -Analysis | MM | 1
| -Scrum Master | MA | 1
Total |  |  | 65

## 31 Maret (1)
Task | D1 | D2 | D3 | D4 | D5 | D6
View Menu | 8 | 4 | 2 | 1
Manage Menu Item | 10 | 5 | 2 | 1
View Picture of Menu | D1: 6; D2: 2
Manage Item Picture | D1: 6; D2: 4; D3: 1
View ingredient of Menu | D1: 6; D2: 4; D3: 1
Manage Menu Ingredient | 8 | 4 | 2 | 1
View menu item duration | D1: 3; D2: 1
Manage item duration | 10 | 5 | 2 | 1
Total | 57 | 29 | 10 | 4

## 31 Maret (2)
Task | PIC | Duration
View Menu | DJ, YA, OI | 8
Manage Menu Item | DJ, YA, KV, OI | 10
View Picture of Menu | DJ, OI | 6
Manage Item Picture | KV, YA, OI | 6
View ingredient of Menu | DJ, YA, OI | 6
Manage Menu Ingredient | DJ, YA, KV, OI | 8
View menu item duration | DJ, OI | 3
Manage item duration | DJ, KV, YA, OI | 10
Total |  | 57